- Framework for Management and Control

In Software Project Management (SPM), the Framework for Management and Control is the systematic process used to monitor project performance, compare actual progress with the approved plan, identify deviations, and take corrective action.

The core idea is:

Plan → Collect Data → Measure Progress → Compare with Baseline → Identify Variance → Take Corrective Action → Report → Re-plan if Required

A project-control framework commonly monitors scope, effort, cost, schedule, quality, risks, and changes throughout the project. PMI describes the control cycle similarly: update plans and status, analyze risks, monitor variances, publish corrective actions/changes, and communicate with stakeholders

Basic Management and Control Cycle

PROJECT PLAN

↓

Establish Baseline

↓

Execute Project

↓

Collect Data

↓

Measure Actual Progress

↓

Compare with Baseline

↓

┌─────────┴─────────┐

↓                   	                            ↓

No Major Variance    Variance Found

↓                    	                             ↓

Continue Project      Analyze Cause

↓

Corrective Action

↓

Update/Re-plan

↓

Monitor Again

Main Components of the Framework

The framework can be studied through the following components:

- Creating the Management and Control Framework

- Collection of Data

- Visualizing Progress

- Cost Monitoring

- Earned Value Analysis

- Prioritizing Monitoring

- Project Tracking

- Change Control

- Software Configuration Management

- Managing Contracts

- Contract Management

- Creating the management and control framework

Before monitoring begins, the project manager needs to establish what will be monitored, how it will be measured, who will collect the information, and when it will be reviewed.

Important activities

A. Establish the baseline

The baseline is the approved version of the project plan against which actual performance is compared.

It normally includes:

- Scope

- Schedule

- Cost

- Effort

- Quality targets

- Milestones

- Resources

For example:

| Parameter | Planned |
| --- | --- |
| Project duration | 6 months |
| Budget | ₹20 lakh |
| Team | 10 people |
| Major modules | 8 |
| Testing period | 1 month |

This becomes the reference point for control.

B. Define checkpoints

A checkpoint is a predetermined point at which project progress is reviewed.

Two common types are:

Time-driven checkpoint:
Review every Friday.

Event-driven checkpoint:
Review when a major milestone such as "Design Complete" is achieved.

SPM teaching material commonly identifies both time-driven and event-driven checkpoints for progress assessment.

C. Define reporting frequency

Different management levels may require different reporting frequencies.

For example:

- Developer → daily

- Project manager → weekly

- Senior management → monthly

- Client → milestone-based

D. Define responsibilities

The framework should specify:

- Who collects data?

- Who checks the data?

- Who prepares reports?

- Who analyzes deviations?

- Who approves corrective action?

- Collecting the data

After establishing the framework, the project manager needs actual project data.

Data collection provides the factual information required for monitoring and control.

Types of data

1. Schedule data

- Planned completion date

- Actual completion date

- Delays

- Milestones completed

- Remaining work

2. Effort data

- Hours worked

- Developer effort

- Testing effort

- Actual effort vs estimated effort

3. Cost data

- Labour cost

- Hardware/software cost

- Cloud cost

- Other project expenses

4. Quality data

- Number of defects

- Severity of defects

- Test cases passed/failed

- Rework

5. Resource data

- People assigned

- Resource utilization

- Availability

- Skill requirements

6. Risk data

- Existing risks

- New risks

- Risk probability

- Risk impact

- Mitigation status

7. Change data

- New requirements

- Changed requirements

- Approved changes

- Rejected changes

Sources

Data may come from:

- Timesheets

- Progress reports

- Meetings

- Issue trackers

- Version-control systems

- Testing systems

- Customer feedback

- Financial records

A project monitoring system should also establish who collects data, how often it is collected, where it is stored, and who receives the resulting reports.

- Visualizing the progress

Raw data can be difficult to understand. Therefore, project information is converted into charts, graphs, dashboards, and visual indicators.

Common techniques

A. Gantt Chart

Shows activities against time.

Task              Week 1  2  3  4  5  6

Requirements       ██████

Design                    ███████

Coding                         ███████████

Testing                              ███████

It helps identify:

- Current progress

- Delayed activities

- Dependencies

- Upcoming tasks

B. Progress Bar

Example:

Development: 70%

██████████████░░░░░░

C. Milestone Chart

Shows major achievements:

Requirements ✓

↓

Design ✓

↓

Coding → 70%

↓

Testing

↓

Deployment

D. RAG/Traffic-Light Reporting

Tasks can be categorized as:

- 🟢 Green – On target

- 🟠 Amber – Problem exists but recoverable

- 🔴 Red – Serious deviation requiring attention

RAG reporting and Gantt/progress visualization are specifically discussed in SPM teaching material for monitoring project status.

E. Burndown Chart

Commonly used in Agile projects.

It shows remaining work against time.

- Cost Monitoring

Cost monitoring means continuously comparing actual expenditure with planned expenditure.

Costs may include:

- Employee salaries

- Software licenses

- Hardware

- Cloud services

- Training

- Outsourcing

- Infrastructure

Example

Suppose:

Planned expenditure after 3 months = ₹8 lakh

Actual expenditure = ₹9 lakh

Then:

Cost Variance=Planned Cost-Actual Cost
=8-9=-₹1 lakh

The project is spending more than planned at this point.

The manager must investigate:

- Why did the cost increase?

- Was additional effort required?

- Were requirements changed?

- Were resources used inefficiently?

- Is the budget estimate still realistic?

8. Earned Value Analysis (EVA)

Earned Value Analysis is an important technique for measuring project performance by relating planned work, completed work, and actual cost.

Three important values are:

PV — Planned Value

Value of work that should have been completed according to the plan.

EV — Earned Value

Value of work that has actually been completed.

AC — Actual Cost

Actual money spent for the completed work.

Schedule Performance Index

SPI=EVPV

Interpretation:

- SPI = 1 → On schedule

- SPI < 1 → Behind schedule

- SPI > 1 → Ahead of schedule

Cost Performance Index

CPI=EVAC

Interpretation:

- CPI = 1 → Cost performance as planned

- CPI < 1 → Cost efficiency is worse than planned

- CPI > 1 → Cost efficiency is better than planned

EVA is therefore useful for identifying schedule and cost problems before they become larger issues.

- Prioritizing Monitoring

It is not practical to monitor every project activity with the same intensity.

The project manager should focus more attention on critical and high-risk activities.

High-priority activities may include:

- Critical path activities

- High-cost activities

- High-risk activities

- Activities with major dependencies

- Activities close to important milestones

- Activities already showing significant delays

For example:

Suppose there are 100 project tasks but only 10 are on the critical path.

Those 10 tasks deserve particularly close monitoring because their delay can affect the overall project completion date.

- Project Tracking

Project tracking means continuously comparing actual project performance with the project plan.

The manager tracks:

- Scope

- Schedule

- Cost

- Effort

- Quality

- Resources

- Risks

A simple tracking table can be:

| Activity | Planned | Actual | Status |
| --- | --- | --- | --- |
| Requirements | 100% | 100% | 🟢 |
| UI Design | 100% | 90% | 🟠 |
| Backend | 80% | 60% | 🔴 |
| Testing | 20% | 10% | 🟠 |

This immediately shows where management attention is required.

PMI's project-control framework similarly emphasizes comparing actual scope, effort, cost, and schedule against the baseline and taking corrective action when plans are not being met.